## Ark1
GANTT Diagram |  |  | To use the template click File and make a copy | [24 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Fjernvarme Optimering |  |  |  |  | COMPANY NAME
| PROJECT MANAGER | Daniel Thisted Larsen |  |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO
|  | TASK TITLE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 | [5 empty] | WEEK 6
|  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F |  | M | T | W | R | F
Ide udvikling | bar: WEEK 1 M to WEEK 2 F
Problemformulering | bar: WEEK 2 F to WEEK 3 R
Scrum | bar: WEEK 2 T to WEEK 5 F
Gantt | bar: WEEK 1 M to WEEK 3 W
WBS | bar: WEEK 2 T to WEEK 3 W
Business model canvas | bar: WEEK 2 F to WEEK 3 F
Risikoanalyse | bar: WEEK 2 F to WEEK 3 F
Interessantanalyse | bar: WEEK 2 F to WEEK 3 F
Produktudvikling | bar: WEEK 3 W to WEEK 5 F
Kravtest | bar: WEEK 4 R to WEEK 5 R
HTML, flask og CSS | bar: WEEK 3 W to WEEK 5 F
Flowchart
Blok diagram | bar: WEEK 2 F to WEEK 3 W
BOM liste | bar: WEEK 2 F to WEEK 3 M
Test af løsning
Konklusion
Resume
Perspektivering